## Team
Name | Rolle | Level | Wochenstunden | Stundensatz (€) | Jira-Projekt | Skills
Petra Hartmann | Tech Lead | Principal | 40 | 115 | PLATFORM, MOBILE | Architektur, Java, Kotlin, Review
Stefan Reiter | Backend Dev | Senior | 40 | 98 | PLATFORM | Java, Spring Boot, Kafka, PostgreSQL
Miriam Yilmaz | Backend Dev | Professional | 32 | 88 | PLATFORM | Go, gRPC, Redis
Felix Lange | Frontend Dev | Senior | 40 | 92 | MOBILE | React Native, TypeScript, Swift
Claudia Berger | Frontend Dev | Professional | 40 | 82 | MOBILE | React Native, JavaScript, Figma
Tobias Engel | Fullstack Dev | Senior | 40 | 90 | PLATFORM, MOBILE | Node.js, React, Docker, PostgreSQL
Anja Krüger | DevOps Engineer | Expert | 40 | 105 | PLATFORM, MOBILE | Kubernetes, Terraform, AWS, GitLab CI
Dennis Wolf | SRE / Ops | Expert | 40 | 100 | PLATFORM | Monitoring, Grafana, Incident Response, Linux
Lena Schuster | QA Lead | Senior | 40 | 88 | PLATFORM, MOBILE | Testplanung, Cypress, Appium, Teststrategie
Patrick Vogel | QA Engineer | Professional | 40 | 72 | PLATFORM | API-Tests, Postman, k6, Jest
Simone Kraft | QA Engineer | Professional | 30 | 70 | MOBILE | Mobile Testing, Appium, BrowserStack
Moritz Hahn | Backend Dev | Junior | 40 | 62 | PLATFORM | Java, Spring Boot (in Einarbeitung)

## Urlaub & Abwesenheiten
Name | Typ | Von | Bis | Tage | Genehmigt | Kommentar
Petra Hartmann | Konferenz | 2026-03-18 | 2026-03-20 | 3 | Ja | KubeCon EU
Petra Hartmann | Urlaub | 2026-04-06 | 2026-04-10 | 5 | Ja
Stefan Reiter | Krank | 2026-03-09 | 2026-03-13 | 5 | - | Rücken-OP Nachsorge
Stefan Reiter | Urlaub | 2026-04-13 | 2026-04-24 | 10 | Ja | Familienurlaub
Miriam Yilmaz | Urlaub | 2026-03-23 | 2026-04-03 | 10 | Ja | Osterurlaub Türkei
Felix Lange | Fortbildung | 2026-03-16 | 2026-03-17 | 2 | Ja | React Native Advanced Workshop
Felix Lange | Urlaub | 2026-05-11 | 2026-05-22 | 10 | Beantragt
Claudia Berger | Mutterschutz | 2026-05-01 | 2026-08-31 | 88 | Ja | Mutterschutz + Elternzeit
Tobias Engel | Urlaub | 2026-03-30 | 2026-04-03 | 5 | Ja | Osterferien
Anja Krüger | Urlaub | 2026-04-20 | 2026-05-01 | 10 | Ja
Anja Krüger | Konferenz | 2026-03-18 | 2026-03-20 | 3 | Ja | KubeCon EU (mit Petra)
Dennis Wolf | Bereitschaft | 2026-03-16 | 2026-03-27 | 10 | - | On-Call Rotation, 50% Kapazität
Dennis Wolf | Urlaub | 2026-04-06 | 2026-04-10 | 5 | Ja
Lena Schuster | Fortbildung | 2026-04-01 | 2026-04-02 | 2 | Ja | ISTQB Advanced
Patrick Vogel | Urlaub | 2026-03-23 | 2026-03-27 | 5 | Ja
Simone Kraft | Kind krank | 2026-03-11 | 2026-03-13 | 3 | -
Simone Kraft | Urlaub | 2026-04-06 | 2026-04-17 | 10 | Ja | Osterferien Kinder
Moritz Hahn | Fortbildung | 2026-03-25 | 2026-03-27 | 3 | Beantragt | Java Spring Bootcamp intern

## Sprint-Kapazität
Sprint | Von | Bis | Arbeitstage | Team-Kapazität (h) | Geplant (SP) | Erledigt (SP) | Velocity | Bemerkung
Sprint 2026-05 | 2026-02-03 | 2026-02-14 | 10 | 420 | 58 | 52 | 52
Sprint 2026-06 | 2026-02-17 | 2026-02-28 | 10 | 420 | 55 | 56 | 56
Sprint 2026-07 | 2026-03-02 | 2026-03-13 | 10 | 356 | 50 | 44 | 44 | Stefan krank, Simone Kind krank
Sprint 2026-08 | 2026-03-16 | 2026-03-27 | 10 | 296 | 42 |  |  | KubeCon, On-Call Dennis, Miriam+Patrick Urlaub
Sprint 2026-09 | 2026-03-30 | 2026-04-10 | 9 | 252 |  |  |  | Ostern, viele Abwesenheiten
Sprint 2026-10 | 2026-04-13 | 2026-04-24 | 10 | 264 |  |  |  | Stefan+Anja Urlaub
Sprint 2026-11 | 2026-04-27 | 2026-05-08 | 9 | 228 |  |  |  | 1. Mai, Claudia geht in Mutterschutz