## Team
Name | Rolle | Level | Wochenstunden | Stundensatz (€) | Jira-Projekt | Skills
Lisa Müller | Backend Dev | Senior | 40 | 95 | BACKEND | Java, Spring, PostgreSQL
Tom Schneider | Frontend Dev | Professional | 32 | 85 | FRONTEND | React, TypeScript, CSS
Anna Weber | Fullstack Dev | Senior | 40 | 90 | BACKEND, FRONTEND | Node.js, React, Docker
Markus Fischer | DevOps Engineer | Expert | 40 | 100 | BACKEND | Kubernetes, Terraform, CI/CD
Sarah Klein | Frontend Dev | Junior | 40 | 65 | FRONTEND | React, JavaScript
Jan Hoffmann | Backend Dev | Professional | 24 | 88 | BACKEND | Python, FastAPI, PostgreSQL
Nina Braun | QA Engineer | Professional | 30 | 78 | BACKEND, FRONTEND | Cypress, Jest, Testplanung
Kai Schmidt | Tech Lead | Principal | 40 | 110 | BACKEND, FRONTEND | Architektur, Java, Review

## Urlaub & Abwesenheiten
Name | Typ | Von | Bis | Tage | Genehmigt | Kommentar
Lisa Müller | Urlaub | 2026-03-23 | 2026-04-03 | 10 | Ja | Osterurlaub
Lisa Müller | Fortbildung | 2026-04-20 | 2026-04-21 | 2 | Ja | AWS Zertifizierung
Tom Schneider | Urlaub | 2026-03-16 | 2026-03-20 | 5 | Ja
Anna Weber | Krank | 2026-03-10 | 2026-03-12 | 3 | - | Krankmeldung liegt vor
Anna Weber | Urlaub | 2026-04-06 | 2026-04-17 | 10 | Ja
Markus Fischer | Urlaub | 2026-04-13 | 2026-04-17 | 5 | Ja
Sarah Klein | Fortbildung | 2026-03-25 | 2026-03-27 | 3 | Beantragt | React Conf Berlin
Jan Hoffmann | Elternzeit | 2026-05-01 | 2026-06-30 | 43 | Ja | 2 Monate Elternzeit
Nina Braun | Urlaub | 2026-03-30 | 2026-04-03 | 5 | Ja | Osterferien Kinder
Kai Schmidt | Konferenz | 2026-04-08 | 2026-04-10 | 3 | Ja | WeAreDevelopers Berlin

## Sprint-Kapazität
Sprint | Von | Bis | Arbeitstage | Team-Kapazität (h) | Geplant (SP) | Erledigt (SP) | Velocity
Sprint 2026-05 | 2026-02-03 | 2026-02-14 | 10 | 280 | 42 | 38 | 38
Sprint 2026-06 | 2026-02-17 | 2026-02-28 | 10 | 264 | 40 | 41 | 41
Sprint 2026-07 | 2026-03-02 | 2026-03-13 | 10 | 232 | 38 | 35 | 35
Sprint 2026-08 | 2026-03-16 | 2026-03-27 | 10 | 208 | 34
Sprint 2026-09 | 2026-03-30 | 2026-04-10 | 9 | 180
Sprint 2026-10 | 2026-04-13 | 2026-04-24 | 10 | 168